## Sheet1
PROJECT PLAN, GRANT BUDGET AND MEDIA PLAN (APPENDIX A) 2026/2027 (Round 7)
Project Title:Nyack Youth Music Festival in Memorial Park | [7 empty] | Contact Name/Cell Phone: Mary Decker, 1-(845) 535-3033
Project Plan (outline major milestones, costs not covered by Nyack Tourism Grant) | 2026-07-25 | 2026-08-25 | 2026-09-25 | 2026-10-25 | 2026-11-25 | 2026-12-25 | 2027-01-26 | 2027-02-26 | 2027-03-26 | 2027-04-26 | 2027-05-26 | 2027-06-26 | COST | FINANCE SOURCE
Secure venue | x | [11 empty] | 0
Secure sponsorships | x | x
Secure Acts | x | x | [10 empty] | 8000 | Sponsorships
Run marketing campaign |  |  | x | x | [8 empty] | 5500 | Nyack Tourism Grant
TOTAL | [12 empty] | 13500
MEDIA PAID FOR BY GRANT | 2026-07-25 | 2026-08-25 | 2026-09-25 | 2026-10-25 | 2026-11-25 | 2026-12-25 | 2027-01-26 | 2027-02-26 | 2027-03-26 | 2027-04-26 | 2027-05-26 | 2027-06-26 | COST
Printed Media (Flyers, Posters, etc.) incl. Design - Cost: | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750
Details: Festival Poster, Design and Print
Paid Social Media Campaign - Cost: | 0 | 750 | 750 | 750 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250
Details:FB, IG, TikTok, NYC Metro Area, age group 14-65
Radio media (:30 second audio ads) - Cost: | 0 | 600 | 0 | 600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200
Details:WHUD, The Peak, etc, NYC Metro Area, Age group 14-65
PR/Press release/outreach - cost: | 0 | 0 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
Details: Press release and press pitch, NYC Metro Area
Other Marketing Costs: | 0 | 0 | 150 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300
Details: Email blasts, NYC Metro Area
[11 empty] | Total |  | 5500